## List
Sub Basin | Project Name | County | ST | Project Type | Property Type | Landowner /Mgr | Financial Partners | Status | Cost Low | Cost High | Funding Status | Description | Community Workday | Who added/ commented
Alder Creek Basin | Alder Creek Watershed | Nevada | CA | Assessment | Both | Multiple |  | Not started | 0 | 50000 | Not funded
Alder Creek Basin | Emigrant Trail | Nevada | CA | Design | Public | USFS |  | Not started |  |  | Not funded |  | yes
Alder Creek Basin | Prosser Lake View- Emigrant Trail | Nevada | CA | Implementation | Public | USFS |  | Not started |  |  | Not funded | Trail restoration | yes | LW
Alder Creek Basin | Prosser Lake View- Emigrant Trail | Nevada | CA | Design | Public | USFS |  | Not started |  |  | Not funded | Trail restoration |  | LW
Alder Creek Basin | Trail Crossings and Trail Maintenance (Alder Rd Reach) | Nevada | CA | Design | Public | USFS |  | Not started | 0 | 50000 | Not funded | Current conditions: Tahoe National Forest non-motorized system trails cross Alder Creek in five locations. The Commemorative Overland Emigrant Trail (COET) crossed Alder Creek four times; the Prosser Lakeview Trail crossed Alder Creek once. Project description: All five crossings are in need of new hardened stream crossings. The four crossings of the COET will be constructed into hardened stream crossings to National Forest Service standards. The fifth crossing on the Prosser Lakeview Trail will involve a small (less than 1/4 mi) re-route and a hardened shallow stream crossing. Obliteration and rehabilitation of the old trail will include the removal of a failing embankment and revegetation.
Alder Creek Basin | Trail Crossings and Trail Maintenance (Alder Rd Reach) | Nevada | CA | Implementation | Public | USFS |  | Not started |  |  | Not funded |  |  | LW
Alder Creek Basin | Upper Commemorative Overland Emigrant Trail Re-Routing | Nevada | CA | Design | Public | USFS |  | Not started | 0 | 50000 | Not funded | Current conditions: The upper portion of the trail, from the trail's beginning termini to its crossing of Alder Creek rd., is severely degraded, does not meet Forest Service erosion-control standards, and unsafely crosses Alder Creek four times without properly engineered crosssings. Project description: Two bridges and a major trail re-route will be constructed to accomodate the early-season use patterns that correspond with early season peak creek flows. The two additional historic crossings and former trail will be rehabilitaed.
Bear Creek Basin | Alpine Meadows Ski Area Erosion | Placer | CA | Design | Both | Alpine Meadows Squaw Valley |  | Not started | 0 | 50000 | Not funded
Bear Creek Basin | Bear Creek Watershed | Placer | CA | Assessment | Both | Alpine Meadows, HOA, Placer County, USFS |  | Not started | 0 | 50000 | Not funded |  |  | LW
Bear Creek Basin | Bear Creek Watershed | Placer | CA | Assessment | Both | Multiple |  | Not started | 0 | 50000 | Not funded
Big Chief Corridor | Alpine Meadows Bridge Replacement | Placer | CA |  |  |  | Caltrans, Placer County Co |  |  |  |  | check on these |  | SM - DOT
Big Chief Corridor | First 4 Mile Restoration | Placer | CA | Design | Public | USFS, TCPUD | TCPUD, TRWC, Placer Co | Partially Completed | 50001 | 100000 | Fully funded | Programmatic EIR underway, JH TO ADD COST RANGE |  | LW
Big Chief Corridor | First 4 Mile Restoration | Placer | CA | Implementation | Public | USFS, TCPUD | TCPUD, TRWC | Not started | 100001 | 250000 | Partially funded |  |  | JH
Big Chief Corridor | Truckee River Access Plan | Placer | CA | Assessment | Public | Placer County | Placer CO | Completed | 0 | 50000 | Fully funded
Big Chief Corridor | Truckee River Corridor Access Plan | Placer | CA | Assessment | Public | Numerous | Resort Assoc and Placer County | Partially Completed | 250001 | 500000 | Fully funded | CEQA/NEPA and partial trail design will be completed in 2014. County will seek funding to build trail mid 2014. | No | ed sullivan
Boca Complex | Boca Complex Watershed | Sierra | CA | Assessment | Public | USFS |  | Partially Completed | 0 | 50000 | Partially funded |  | yes
Boca Complex | Boca-Stampede Noxious Weed Management | Nevada | CA | Design | Public | USFS | USFS | Completed | 0 | 50000 | Fully funded | The project entails noxious weed control by hand-pulling of musk thistle and yellow starthistle along the Truckee River, Little Truckee River, Boca Reservoir, Stampede Reservoir and Boca Hill on the Tahoe National Forest. A private contract crew would be hired to pull weeds for approximately 50 person days to assist the Forest Service weed crew hand pull noxious weeds on steep inaccesible terrain. The Truckee River Watershed Council would put out the bids and hire the contractor. In addition the TRWC would plan and outreach for two volunteer weed pull days to reach out to educate and get help from the local community. |  | LW/SU/JH
Boca Complex | Boca-Stampede Noxious Weed Management | Nevada | CA | Implementation | Public | USFS | USFS, TRWC, SIERRA CO | Partially Completed | 100001 | 250000 | Partially funded | The project entails noxious weed control by hand-pulling of musk thistle and yellow starthistle along the Truckee River, Little Truckee River, Boca Reservoir, Stampede Reservoir and Boca Hill on the Tahoe National Forest. A private contract crew would be hired to pull weeds for approximately 50 person days to assist the Forest Service weed crew hand pull noxious weeds on steep inaccesible terrain. The Truckee River Watershed Council would put out the bids and hire the contractor. In addition the TRWC would plan and outreach for two volunteer weed pull days to reach out to educate and get help from the local community. | yes | LW/SU/JH
Boca Complex | Dry Creek Watershed | Nevada | CA | Assessment | Both | USFS | TRWC, USFS | Completed | 0 | 50000 | Fully funded | see assessment; The Dry Creek watershed is tributary to the Little Truckee River via Boca Reservoir. The Dry Creek Watershed has been identified as a degraded watershed from a forest vegetation ecosystem, hydrologic function and soil erosion and sedimentation perspective. The watershed restoration project was initiated to correct these important ecological functions. This project proposes to restore vegetation structure, hydrologic function and controll erosion within the watershed to restore the overall health of the ecosytem within this watershed. |  | LW
Boca Complex | Dry Creek Watershed - Main Channel | Nevada | CA | Design | Public | USFS |  | Not started | 0 | 50000 | Not funded | see assessment, pages 47-51 |  | LW
Boca Complex | Dry Creek Watershed - Main Channel | Nevada | CA | Implementation | Public | USFS |  | Not started | 0 | 50000 | Not funded | see assessment, pages 47-51 |  | LW
Boca Complex | Dry Creek Watershed - Tributary 16 | Nevada | CA | Design | Public | USFS |  | Not started | 0 | 50000 | Not funded | see assessment, pages 47-51 |  | LW
Boca Complex | Dry Creek Watershed - Tributary 16 | Nevada | CA | Implementation | Public | USFS |  | Not started | 0 | 50000 | Not funded | see assessment, pages 47-51 |  | LW
Boca Complex | Dry Creek Watershed - Tributary 1A | Nevada | CA | Design | Public | USFS |  | Not started | 0 | 50000 | Not funded | see assessment, pages 47-51 |  | LW
Boca Complex | Dry Creek Watershed - Tributary 1A | Nevada | CA | Implementation | Public | USFS |  | Not started | 0 | 50000 | Not funded | see assessment, pages 47-51 |  | LW
Boca Complex | Dry Creek Watershed - Tributary 21 | Nevada | CA | Design | Public | USFS |  | Not started | 0 | 50000 | Not funded | see assessment, pages 47-51 |  | LW
Boca Complex | Dry Creek Watershed - Tributary 21 | Nevada | CA | Implementation | Public | USFS |  | Not started | 0 | 50000 | Not funded | see assessment, pages 47-51 |  | LW
Boca Complex | Hoke Valley Watershed | Sierra | CA | Assessment | Public | USFS |  | Not started | 0 | 50000 | Not funded | Hoke Valley drainage is tributary to the Little Truckee River via Stampede Reservoir. Hoke valley has been identified as a degraded watershed for hydrologic function within the stream and meadow areas. An assessment of the watershed is needed to identify, prioritize and develop site specific restoration/enhancement projects. This would lead to the next step of NEPA analysis of selected projects and implementation.
Boca Complex | Kyburz Watershed | Sierra | CA | Assessment | Public | USFS |  | Not started | 50001 | 100000 | Not funded | The Kyburz sub watershed is a small tributary to the Little Truckee River. This watershed has been identified as a degraded for hydrologic function. There is potential to restore the hydrologic function in part of the meadow system and the stream system above and below the meadow. The first step in developing a restoration plan is to complete a watershed assessment to identify watershed issues within the watershed and develop and prioritize restoration/improvement projects.
Boca Complex | LTR Fish Habitat Restoration Project | Sierra | CA | Design | Public | USFS | USFS, TU | Partially Completed | 50001 | 100000 | Not funded |  |  | LW
Boca Complex | LTR Fish Habitat Restoration Project | Sierra | CA | Implementation | Public | USFS | USFS, TU | Not started | 50001 | 100000 | Not funded |  | yes | LW
Boca Complex | Transition Road Decommisioning | Nevada | CA | Design | Public | USFS |  | Completed | 0 | 50000 | Fully funded | An esisting road is scheduled for decomissioinng and two areas where grades have disrupted hydrogic connectivity would be restored. One grade interupts wetland hydrology, The other grade disrupts aspen stand hydrology.
Boca Complex | Transition Road Decommisioning | Nevada | CA | Implementation | Public | USFS |  | Not started |  |  | Not funded
Bronco Creek Basin | Bronco Creek Watershed | Washoe | NV | Assessment | Public | USFS |  | Completed | 0 | 50000 | Fully funded | USFS Humbolt Toiyabe
Cabin Creek Basin | Cabin Creek Watershed | Placer | CA | Assessment | Both | Multiple |  | Not started | 0 | 50000 | Not funded
Coldstream Canyon Basin | Coldstream Canyon | Nevada | CA | Assessment | Public | Multiple | TRWC | Completed | 0 | 100000 | Not funded |  |  | LW
Coldstream Canyon Basin | Coldstream Canyon Floodplain/Lower Alluvial Fan - CDPR | Nevada | CA | Design | Public | CDPR | TRWC, CDPR | Completed | 100001 | 250000 | Fully funded | Assessment, pages 48-50 |  | LW
Coldstream Canyon Basin | Coldstream Canyon Floodplain/Lower Alluvial Fan - CDPR | Nevada | CA | Implementation | Public | CDPR | TRWC, CDPR | Completed | 250001 | 500000 | Fully funded | Assessment, pages 48-50 | yes | LW
Coldstream Canyon Basin | Coldstream Canyon Floodplain/Lower Alluvial Fan - CDPR | Nevada | CA | Post-Project Monitoring | Public | CDPR | TRWC, CDPR | Partially Completed | 0 | 50000 | Fully funded | Assessment, pages 48-50 |  | LW
Coldstream Canyon Basin | Coldstream Canyon Floodplain/Lower Alluvial Fan - Private | Nevada | CA | Design | Private | Private |  | Partially Completed | 0 | 50000 | Partially funded | Assessment, pages 48-50 |  | LW
Coldstream Canyon Basin | Coldstream Canyon Floodplain/Lower Alluvial Fan - Private | Nevada | CA | Implementation | Private | Private |  | Not started | 250001 | 500000 | Not funded | Assessment, pages 48-50 |  | LW
Coldstream Canyon Basin | Lower Valley Gravel Ponds | Nevada | CA | Design | Public | CDPR | TRWC, CDPR | Partially Completed | 0 | 50000 | Partially funded | Test/pilot completed. See Assessment, pages 47, 48 |  | LW
Coldstream Canyon Basin | Lower Valley Gravel Ponds | Nevada | CA | Implementation | Public | CDPR | TRWC, CDPR | Partially Completed | 100001 | 250000 | Partially funded | Test/pilot completed. See Assessment, pages 47, 48 | yes | LW
Coldstream Canyon Basin | Railroad Culvert Modification | Nevada | NV | Design | Both | Multiple |  | Not started | 50001 | 100000 | Not funded | get from Assessment, page 44-45 |  | LW
Coldstream Canyon Basin | Railroad Culvert Modification | Nevada | NV | Implementation | Both | Multiple |  | Not started | 250001 | 250000 | Not funded | get from Assessment, page 44-45 |  | LW
Coldstream Canyon Basin | Upland Areas | Nevada | CA | Design | Both | Multiple |  | Not started | 0 | 50000 | Not funded | get from Assessment, pages 41, 42 |  | LW
Coldstream Canyon Basin | Upland Areas | Nevada | CA | Implementation | Both | Multiple |  | Not started | 50001 | 250000 | Not funded | get from Assessment, pages 41, 42 | yes | Lw
Coldstream Canyon Basin | Upper Valley Woody Debris Placement | Nevada | CA | Design | Public | Multiple |  | Not started | 50001 | 100000 | Not funded | get from Assessment, pages 46-47 |  | LW
Coldstream Canyon Basin | Upper Valley Woody Debris Placement | Nevada | CA | Implementation | Public | Multiple |  | Not started | 0 | 50000 | Not funded | get from Assessment, pages 46-47 |  | LW
Davies-Merrill Creek Basin | Davies Meadow and Riparian, Phase 1 | Sierra | CA | Design | Public | USFS | USFS, TRWC | Completed | 50001 | 100000 | Fully funded | LW TO ADD COSTS |  | LW
Davies-Merrill Creek Basin | Davies Meadow and Riparian, Phase 2 | Sierra | CA | Design | Both | USFS | USFS | Partially Completed |  |  | Partially funded |  |  | LW
Davies-Merrill Creek Basin | Davies Meadow and Riparian, Phase 1 | Sierra | CA | Implementation | Public | USFS | USFS, TRWC | Completed | 100001 | 250000 | Fully funded | LW TO ADD COSTS | yes | LW
Davies-Merrill Creek Basin | Davies Meadow and Riparian, Phase 2 | Sierra | CA | Implementation | Both | USFS |  | Not started |  |  | Not funded | The Davies Creek sub watershed is a tributary to the Little Truckee River via Stampede Reservoir. This watershed has been identified as a degraded for hydrologic function. Phase 1 completed seven stream and meadow restoration projects. There is potential to restore the hydrologic function at several additional site of the meadow and stream systems within the watershed both on FS lands and private lands. The first step in developing a restoration plan is to complete a watershed assessment (partially completed), develop and prioritize restoration/improvement projects, develop site specific restoration plans, complete NEPA assessments and implement the projects. | yes | LW
Davies-Merrill Creek Basin | Jammer Chair Stream and Aspen Restoration | Sierra | CA | Design | Public | USFS | USFS | Completed | 0 | 50000 | Fully funded | The Jammer Chair area is tributary to Davies Creek via Sardine Valley. Two restoration sites have been identified for restoration of hydrologic function and erosion prevention as part of an aspen restoration project. The conifers have been removed and hydrologic restoration plans have been developed. The proposed work includes rille construction and/or filling in the incised gully which will reconect the floodplain, stabilize actively eroding banks, and raise the seasonal water table. This will stop the current erosion and re-water the adjacent aspen stands. |  | LW
Davies-Merrill Creek Basin | Jammer Chair Stream and Aspen Restoration | Sierra | CA | Implementation | Public | USFS |  | Not started | 0 | 50000 | Not funded |  |  | LW
Davies-Merrill Creek Basin | Jones Valley Meadow and Riparian Restoration | Sierra | CA | Design | Public | USFS | USFS, TRWC | Completed | 0 | 50000 | Fully funded | completed with Davie Meadow and Riparian, Phase 1 |  | QY, LW
Davies-Merrill Creek Basin | Jones Valley Meadow and Riparian Restoration | Sierra | CA | Implementation | Public | USFS | USFS, TRWC | Completed | 0 | 50000 | Fully funded | completed with Davie Meadow and Riparian, Phase 1 | yes | QY, LW
Davies-Merrill Creek Basin | Sardine Valley | Sierra | CA | Acquistion | Both | Private |  | Not started | 250001 | 500000 | Not funded |  |  | LW/QY
Deep Creek Basin | Deep Creek Watershed | Placer | CA | Assessment | Private |  |  | Not started | 0 | 50000 | Not funded
Deer Creek Basin | Deer Creek Watershed | Placer | CA | Assessment | Public | USFS |  | Not started | 0 | 50000 | Not funded
Donner Lake Basin | Billy Mack Canyon | Nevada | CA | Acquistion | Private | TDLT |  | Completed | 1000001 | 2000000 | Fully funded | see John Svahn | no | LW
Donner Lake Basin | Billy Mack Canyon | Nevada | CA | Design | Public | TDLT |  | Not started | 1000001 | 2000000 | Not funded | Assessment included in Donner Lake Basin assessment; restoration TBD. Possible impacts from I-80 and I-80 maintenance | yes | LW, JS
Donner Lake Basin | Donner 1 Roadway & Drainage Improvement & Wetland Mitigation | Nevada | CA | Implementation | Public | Caltrans DOT |  | Completed |  |  | Fully funded | Rehabilitate the roadway, update the drainage and improve stormwater treatment. There is onsite mitigation in the form of wetland creation near the Donner Pass interchange. Monitoring for 5 years
Donner Lake Basin | Donner 3 Roadway & Drainage Improvement & Wetland Mitigation | Nevada | CA | Implementation | Public | Caltrans DOT |  | Completed |  |  | Fully funded | Rehabilitate the roadway, update the drainage and improve stormwater treatment. There is onsite mitigation in the form of wetland creation near the Donner Pass interchange. Monitoring for 5 years
Donner Lake Basin | Donner Creek at I-80 and Deerfield | Nevada | CA | Assessment | Both | Multiple |  | Not started | 0 | 50000 | Not funded
Donner Lake Basin | Donner Creek Watershed | Nevada | CA | Assessment | Both | Multiple |  | Not started | 0 | 50000 | Not funded |  |  | LW
Donner Lake Basin | Donner Memorial State Park Expansion | Nevada | CA | Design | Public | CA State Parks |  | Not started |  |  | Not funded
Donner Lake Basin | Emigrant Canyon Road and Trails Watershed Rehabilitation | Nevada | CA | Design | Public | CA State Parks |  | Not started |  |  | Not funded
Donner Lake Basin | Johnson Canyon Restoration Site A | Nevada | CA | Implementation | Private | TDA |  | Not started | 50001 | 100000 | Not funded | see assessment | yes | LW
Donner Lake Basin | Johnson Canyon Restoration Site B | Nevada | CA | Implementation | Private | TDA |  | Not started | 0 | 50000 | Not funded | see assessment | yes | LW
Donner Lake Basin | Johnson Canyon Restoration Site C | Nevada | CA | Implementation | Both | TDA, USFS |  | Not started | 0 | 50000 | Not funded | see assessment | yes | LW
Donner Lake Basin | Johnson Canyon Restoration Site D | Nevada | CA | Implementation | Both | TDA, TDLT |  | Not started | 0 | 50000 | Not funded | see assessment | yes | LW
Donner Lake Basin | Johnson Canyon Restoration Site E - I | Nevada | CA | Implementation | Public | TDLT | TRWC | Partially Completed | 100001 | 250000 | Partially funded | see assessment | yes | LW
Donner Lake Basin | Johnson Canyon Restoration Sites A-I | Nevada | CA | Design | Both | TDLT, USFS, TDA | TRWC | Partially Completed | 50001 | 100000 | Partially funded | see assessment |  | LW
Donner Lake Basin | Johnson Canyon Watershed | Nevada | CA | Acquisition | Public, Private | TDLT | TDLT | Completed | 1000001 | 2000000 | Fully funded | see John Svahn |  | LW, JS
Donner Lake Basin | Johnson Canyon Watershed | Nevada | CA | Assessment | Both | TDLT, USFS, TDA | TRWC | Completed | 0 | 50000 | Fully funded | see assessment |  | LW
Donner Lake Basin | Lake View Canyon Road and Trails Watershed Rehabilitation | Nevada | CA | Design | Public | CA State Parks |  | Not started |  |  | Not funded
Donner Lake Basin | Shoreline Erosion (including piers) | Nevada | ca | Design | Both | Multiple |  | Not started | 50001 | 100000 | Not funded |  |  | LW/js
Donner Lake Basin | Shoreline Erosion (including piers) | Nevada | CA | Implementation | Both | Multiple |  | Not started | 50001 | 100000 | Not funded |  | yes | LW/js
Donner Lake Basin | Summit Creek Restoration | Nevada | CA | Design | Public | CA State Parks, TDLT |  | Not started | 0 | 50000 | Not funded |  |  | LW
Donner Lake Basin | Summit Creek Restoration | Nevada | CA | Implementation | Public | CA State Parks, TDLT |  | Not started | 100001 | 250000 | Not funded |  | yes | LW
Donner Lake Basin | Summit Creek Watershed | Nevada | CA | Assessment | Public | CA State Parks, TDLT | CA State Parks | Partially Completed | 0 | 50000 | Partially funded |  |  | LW
Entire Watershed | Aquatic Invasive Species | Multiple | CA | Implementation | Both | Multiple |  | Partially Completed | 500001 | 1000000 | Partially funded | Commenced 2010 - 75K/year - for 10 years | yes
Entire Watershed | Dispersed Lakeshore Recreation Site Inventory and Rehabilitation | Multiple | CA | Assessment | Public | USFS |  | Not started | 0 | 50000 |  | Current Condition: Six akeshores within theTruckee River Watershed show resource degradadtion due to dipersed recreation activities. Project Description: Survey and inventory dispersed recreation sites on theses six Middle Truckee Watershed lakes inliduing: Warren Lake, Devil's Oven Lake, Lake of the Woods, Azalea Lake, Flora Lake, and Summit Lake. Survey techniques will be modeled after the "rapid assessment" used in monitoring wilderness recreation sites. Create a priority list for rehabilitating degraded lakeshore sites. Begin rehabilitation of rcration sites in order of degredation severity process. **Note: Each lake can be estimated and funded separately. **No NEPA required. Can be implemented in 2013 or 2014.
Entire Watershed | Highway Related Erosion And Restoration Projects | Multiple | CA | Implementation | Public | Multiple |  | Partially Completed |  |  | Partially funded | Hwy 267, I-80, Hwy 89 north of Truckee
Entire Watershed | Post-Burn Noxious Weed Removal |  | CA |  | Public | USFS
Entire Watershed | Post-Burn Revegetation |  | CA |  | Public | USFS
Entire Watershed | Post-Burn Seeding with Native |  | CA |  | Public | USFS
Entire Watershed | Roads Assessment | Multiple | CA | Assessment | Public | USFS |  | Partially Completed | 0 | 50000 | Partially funded
Entire Watershed | Sawtooth Trailhead Improvement | Placer | CA | Design | Public | USFS |  | Not started | 0 | 50000 | Not funded | Current conditions: The Sawtooth trail has become a popular recreation area because of the proximity and variety of uses. Mountain biking and Off-highway vehicle use is the most popular. The trailhead has a small parking area that is insufficient for the amount of use. Possible local partners have offered to maintain the area on a volunteer agreement and provide long-term maintenance. Project description: Picnic tables and trash cans are needed to provide a rest area for the users. An e improvent of parking spaces will be needed .
Entire Watershed | Truckee River Recreation Access | Multiple | CA | Assessment | Public | USFS |  | Not started | 100001 | 250000 | Not funded | Current condition: The East bank of the Truckee River next to the Glenshire bridge receives a large amount of recreational use. As a result, the bank erodes and degrades water quality. Project description: Design and build a small accessible fishing pier, trail, and watercraft launch. Improveme the existing parking lot as well.
Entire Watershed | Waterbars - Post-burn (use burned trees) |  | CA |  | Public | USFS
Glenshire / Union Valley Basin | Canyon Springs Trails erosion control | Nevada | CA | Design | Private | Canyon Springs LLC |  | Not started |  |  | Not funded
Glenshire / Union Valley Basin | Culvert Crossing at Glenshire Dr | Nevada | CA | Design | Public | Town of Truckee |  | Not started |  |  | Not funded |  | yes
Gray Creek Basin | Conifer Regeneration | Multiple | CA | Design | Public | CDFW, USFS | USFS | Completed | 0 | 50000 | Fully funded | get from Joanne R. - get from assessment |  | LW
Gray Creek Basin | Conifer Regeneration | Multiple | CA | Implementation | Public | CDFW, USFS | USFS | Completed | 50001 | 100000 | Fully funded | get from Joanne R. - get from assessment | yes | LW
Gray Creek Basin | Cottonwood and Aspen Regeneration | Multiple | CA | Design | Public | CDFW, USFS |  | Not started |  |  | Not funded | get from assessment |  | LW
Gray Creek Basin | Cottonwood and Aspen Regeneration | Multiple | CA | Implementation | Public | CDFW, USFS |  | Not started |  |  | Not funded | get from assessment | yes | LW
Gray Creek Basin | Fish Passage | Multiple | CA | Design | Both | CDFW, USFS, private |  | Not started | 0 | 50000 | Not funded | get from assessment |  | LW
Gray Creek Basin | Fish Passage | Multiple | CA | Implementation | Both | CDFW, USFS, private |  | Not started | 0 | 50000 | Not funded | get from assessment |  | LW
Gray Creek Basin | Gray Creek Watershed | Multiple | CA | Acquistion | Public | USFS | TDLT, TRWC | Completed | 500001 | 1000000 | Fully funded | check price with John Svahn |  | LW
Gray Creek Basin | Gray Creek Watershed | Multiple | CA | Assessment | Both | Multiple | TRWC | Completed | 0 | 100000 | Fully funded |  | yes | LW
Gray Creek Basin | Logging Road and Skid Decommissioning | Multiple | CA | Design | Public | USFS | TRWC | Completed | 0 | 50000 | Fully funded | get from Beth - get from assessment |  | LW
Gray Creek Basin | Logging Road and Skid Decommissioning | Multiple | CA | Implementation | Public | USFS | TRWC | Completed | 50001 | 100000 | Fully funded | get from Beth - get from assessment | yes | LW
Gray Creek Basin | Logging Road and Skid Decommissioning | Multiple | CA | Post-Project Monitoring | Public | USFS | TRWC | Completed | 0 | 50000 | Fully funded | get from Beth - get from assessment |  | LW
Gray Creek Basin | Noxious Weed Control | Multiple | CA | Design | Both | CDFW, USFS, private |  | Not started | 0 | 50000 | Not funded | get from assessment: includes mapping existing populations; coordinate with I-80 Corridor noxious weed control project |  | LW
Gray Creek Basin | Noxious Weed Control | Multiple | CA | Implementation | Both | CDFW, USFS, private |  | Not started | 0 | 50000 | Not funded | get from assessment; includes treatment and annual mapping for three years | yes | LW
I-80 Corridor | Boca-Floriston Roadway & Drainage Improvements | Nevada | CA | Implementation | Public | Caltrans DOT |  | Completed |  |  | Fully funded | Rehabilitate the roadway, update the drainage and improve stormwater treatment. The project is restoring temporary impacts to waters and riparian. Monitoring for 5 years
I-80 Corridor | Boca-Floriston Roadway & Drainage Improvements | Nevada | CA | Implementation | Public | Caltrans DOT |  | Completed |  |  | Fully funded | As part of the Boca-Floriston project, Caltrans installed 5 wildlife crossing features: 3 12x12 natural bottom box culverts and 2 highwater benches. Caltrans has completed monitoring of all 5 structures. 4 of the 5 are working with an annual increase of use. Caltrans is evaluating measures to improve the structure currently not functioning.
I-80 Corridor | Hirschdale Bridge Replacement | Nevada | CA | Design |  |  | Caltrans, Nevada Co | Partially Completed |  |  |  | check on these |  | SM - DOT
I-80 Corridor | I-80 Corridor Watershed | Multiple | CA | Assessment | Public | CDFW |  | Not started | 0 | 50000 | Not funded |  |  | LW
I-80 Corridor | I-80 Corridor Watershed Noxious Weed Control | Multiple | CA | Design | Public | CDFW |  | Not started | 0 | 50000 | Not funded | ASK KRIS KUYPER includes mapping existing populations; coordinate with I-80 Corridor noxious weed control project |  | LW
I-80 Corridor | I-80 Corridor Watershed Noxious Weed Control | Multiple | CA | Implementation | Public | CDFW | SBC, Washoe County Dept. of Regional Parks and Open Space | Completed | 100001 | 250000 | Fully funded | Named "Martis Project" - includes treatment and annual mapping for three years | yes | LW
Independence Lake Basin | Bridge replacement | Sierra | CA | Implementation | Public | TNC,Sierra Co | Sierra, TNC | Partially Completed |  |  | Fully funded |  |  | LW
Independence Lake Basin | Delta and spawning grounds | Sierra | CA | Design | Public, Private | USFS | TNC, TRWC | Completed | [5 empty] | LW/QY
Independence Lake Basin | Delta and spawning grounds | Nevada | CA | Implementation | Both | USFS | TNC, TRWC | Completed |  |  | Fully funded | spawning gravel | yes | LW/QY
Independence Lake Basin | Fish Barrier | Sierra | CA | Implementation | Public | TNC | TNC, TRWC | Completed |  |  | Fully funded |  |  | LW
Independence Lake Basin | Independence Lake Bridge Replacement | Nevada | CA |  |  |  | Caltrans, Sierra Co |  |  |  |  | check on these |  | SM - DOT
Independence Lake Basin | Independence Lake Trail | Nevada | CA | Design | Public | USFS, TNC |  | Partially Completed |  |  | Not funded | Current conditions: With Independence Lake now open to the public, shoreline pedestrian use has increased significantly. A user-created trail circum-navigates the lake with a shallow water crossing through Independence Creek just upstream of its confluence with Independence Lake. This portion of the creek, however, provides important spawning habitat for Lahontan Cutthroat Trout. Project description: The user-created trail near the creek should be obliterated, and a new trail contructed crossing the creek upstream of a waterfall (natural fish barrier) for viewing and avoiding the spawning habitat. |  | LW/QY
Independence Lake Basin | Independence Lake Trail | Sierra | CA | Implementation | Public | USFS |  | Not started | [5 empty] | LW/QY
Independence Lake Basin | Independence Lake Watershed | Nevada | CA | Assessment | Both | Multiple |  | Not started | 0 | 50000 | Not funded
Independence Lake Basin | Independence Tributary Restoration | Sierra | CA | Assessment | Public | USFS |  | Completed | 0 | 50000 | Fully funded | This project is on tributaries to Independence Creek. This watershed has been identified as over threshold and the tributary is impacted from previous railroad grade and logging practices that have affected the sream geomorphology. There is potential to restore the hydrologic function in parts of the meadow system and the stream system tributary to the mainstem of independence creek. These streams contain habitat and identified T&E species (frogs) There are oportunities to collaborate witht the county to improve road interaction with meadows and streams in this area. The first step in developing a restoration plan is to complete a watershed assessment of the two HUC7 watersheds that incompass the area to identify watershed issues within the watershed and develop and prioritize restoration/improvement projects. Once the assements are completed identified projects for watershed improvement will be prioritized, developed/designed, permitted, and then will be ready for implementation.
Independence Lake Basin | Independence Tributary Restoration | Sierra | CA | Design | Public | USFS |  | Completed |  |  | Fully funded
Independence Lake Basin | Independence Tributary Restoration | Sierra | CA | Implementation | Public | USFS |  | Completed |  |  | Fully funded |  | yes
Independence Lake Basin | Self-Reproducing LCT Management | Multiple | CA | Post-Project Monitoring | Public | USFS | USGS | Partially Completed | 0 | 50000 | Partially funded | annual monitoring cost |  | LW
Juniper Creek Basin | Juniper Creek Watershed | Nevada | CA | Assessment | Both | Multiple |  | Not started | 0 | 50000 | Not funded
Martis Creek Basin | Elizabeth Town | Placer | CA | Design | Public | TDLT | TRWC, TDLT | Partially Completed | 0 | 50000 | Partially funded | See assessment, table 10, |  | LW
Martis Creek Basin | Elizabeth Town | Placer | CA | Implementation | Public | TDLT | TRWC, TDLT | Not started | 0 | 50000 | Not funded | See assessment, ?Project 7, Figure 30 |  | LW
Martis Creek Basin | Martis Creek Watershed | Placer | CA | Assessment | Both | Multiple | TRWC | Completed | 50001 | 100000 | Fully funded | see assessment |  | LW
Martis Creek Basin | Martis WLA Ck Diversion Dam Removal | Placer | CA | Implementation | Public | ACOE | ACOE | Not started | 50001 | 100000 |  |  |  | LW, JZ
Martis Creek Basin | Middle Martis Creek | Placer | CA | Design | Public | Multiple | TRWC, TTAD | Partially Completed | 250001 | 500000 | Partially funded | See assessment, Project 11, Figure 34 |  | LW
Martis Creek Basin | Middle Martis Creek | Placer | CA | Implementation | Public | Multiple | TRWC, TTAD, NCSD, CalTrans | Not started | 500001 | 1000000 | Not funded | See assessment, Project 11, Figure 34 |  | Lw
Martis Creek Basin | Project 1 | Placer | CA | Design |  |  |  | Not started | 0 | 50000 | Not funded | See assessment, table 10 |  | LW
Martis Creek Basin | Project 1 | Placer | CA | Implementation |  |  |  | Not started | 50001 | 100000 | Not funded | See assessment, table 10 |  | LW
Martis Creek Basin | Project 10 | Placer | CA | Design |  |  |  | Not started | 0 | 50000 | Not funded | See assessment, table 10 |  | LW
Martis Creek Basin | Project 10 | Placer | CA | Implementation |  |  |  | Not started | 50001 | 100000 | Not funded | See assessment, table 10 |  | LW
Martis Creek Basin | Project 12 | Placer | CA | Design |  |  |  | Not started | 100001 | 250000 | Not funded | Borrow pits, See assessment, table 10 |  | LW
Martis Creek Basin | Project 12 | Placer | CA | Implementation |  |  |  | Not started | 500001 | 1000000 | Not funded | Borrow pits, fish passage, See assessment, table 10 |  | LW
Martis Creek Basin | Project 13 | Placer | CA | Design |  |  |  | Not started | 0 | 50000 | Not funded | See assessment, table 10 |  | LW
Martis Creek Basin | Project 13 | Placer | CA | Implementation |  |  |  | Not started | 50001 | 100000 | Not funded | See assessment, table 10 |  | LW
Martis Creek Basin | Project 14 | Placer | CA | Design |  |  |  | Not started | 0 | 50000 | Not funded | See assessment, table 10 |  | LW
Martis Creek Basin | Project 14 | Placer | CA | Implementation |  |  |  | Not started | 50001 | 100000 | Not funded | See assessment, table 10 |  | LW
Martis Creek Basin | Project 15 | Placer | CA | Design |  |  |  | Not started | 0 | 50000 | Not funded | See assessment, table 10 |  | LW
Martis Creek Basin | Project 15 | Placer | CA | Implementation |  |  |  | Not started | 50001 | 100000 | Not funded | See assessment, table 10 |  | LW
Martis Creek Basin | Project 16 | Placer | CA | Design |  |  |  | Not started | 0 | 50000 | Not funded | See assessment, table 10 |  | LW
Martis Creek Basin | Project 16 | Placer | CA | Implementation |  |  |  | Not started | 50001 | 100000 | Not funded | See assessment, table 10 |  | LW
Martis Creek Basin | Project 17 | Placer | CA | Design |  |  |  | Not started | 0 | 50000 | Not funded | See assessment, table 10 |  | LW
Martis Creek Basin | Project 17 | Placer | CA | Implementation |  |  |  | Not started | 50001 | 100000 | Not funded | See assessment, table 10 |  | LW
Martis Creek Basin | Project 2 | Placer | CA | Design |  |  |  | Not started | 0 | 50000 | Not funded | See assessment, table 10 |  | LW
Martis Creek Basin | Project 2 | Placer | CA | Implementation |  |  |  | Not started | 50001 | 100000 | Not funded | See assessment, table 10 |  | LW
Martis Creek Basin | Project 3 | Placer | CA | Design |  |  |  | Not started | 0 | 50000 | Not funded | See assessment, table 10 |  | LW
Martis Creek Basin | Project 3 | Placer | CA | Implementation |  |  |  | Not started | 50001 | 100000 | Not funded | See assessment, table 10 |  | LW
Martis Creek Basin | Project 4 | Placer | CA | Design |  |  |  | Not started | 0 | 50000 | Not funded | See assessment, table 10 |  | LW
Martis Creek Basin | Project 4 | Placer | CA | Implementation |  |  |  | Not started | 50001 | 100000 | Not funded | See assessment, table 10 |  | LW
Martis Creek Basin | Project 5 | Placer | CA | Design |  |  |  | Not started | 0 | 50000 | Not funded | See assessment, table 10 |  | LW
Martis Creek Basin | Project 5 | Placer | CA | Implementation |  |  |  | Not started | 50001 | 100000 | Not funded | See assessment, table 10 |  | LW
Martis Creek Basin | Project 6 | Placer | CA | Design |  |  |  | Not started | 0 | 50000 | Not funded | See assessment, table 10 |  | LW
Martis Creek Basin | Project 6 | Placer | CA | Implementation |  |  |  | Not started | 50001 | 100000 | Not funded | See assessment, table 10 |  | LW
Martis Creek Basin | Project 7 - dupe with E-Town? | Placer | CA | Design |  |  |  | Not started |  |  | Not funded | See assessment, table 10 |  | LW
Martis Creek Basin | Project 7 - dupe with E-Town? | Placer | CA | Implementation |  |  |  | Not started |  |  | Not funded | See assessment, table 10 |  | LW
Martis Creek Basin | Project 8 | Placer | CA | Design |  |  |  | Not started | 0 | 50000 | Not funded | See assessment, table 10 |  | LW
Martis Creek Basin | Project 8 | Placer | CA | Implementation |  |  |  | Not started | 50001 | 100000 | Not funded | See assessment, table 10 |  | LW
Martis Creek Basin | Project 9 | Placer | CA | Design |  |  |  | Not started | 0 | 50000 | Not funded | See assessment, table 10 |  | LW
Martis Creek Basin | Project 9 | Placer | CA | Implementation |  |  |  | Not started | 50001 | 100000 | Not funded | See assessment, table 10 |  | LW
Mystic Canyon Basin | Mystic Canyon Watershed | Washoe | NV | Assessment | Public | USFS |  | Not started | 0 | 50000 | Not funded
Pole Creek Basin | Pole Creek Watershed | Placer | CA | Assessment | Public | USFS |  | Not started | 50001 | 100000 | Not funded | Pole Creek is a tributary to the Truckee River and is a Lahontan Cutthroat Trout reintroduction site. A lot of work has been completed to reduce sediment production from the road system in this watershed. An assessment is need to identify addition projects to continue this work.
Prosser Creek Basin | Alder Drive Roundabout | Nevada | CA | Implementation | Public | Town of Truckee | Town of Truckee | Completed |  |  | Fully funded | Roundabout at Alder Drive/highway 89
Prosser Creek Basin | Backyard Trail – Prosser Lakeview | Nevada | CA | Design | Public | USFS |  | Partially Completed | 50001 | 100000 | Partially funded |  |  | LW
Prosser Creek Basin | Backyard Trail – Prosser Lakeview | Nevada | CA | Implementation | Public | USFS |  | Not started | 50001 | 100000 | Not funded |  | yes | LW
Prosser Creek Basin | Below the Dam Fish Habitat Enhancement | Nevada | CA | Design | Public | USFS | USFS, TRWC | Completed |  |  | Fully funded | LW TO ADD - Instream habitat restoration, stream bank stabilization | yes | LW
Prosser Creek Basin | Below the Dam Fish Habitat Enhancement | Nevada | CA | Implementation | Public | USFS | USFS, TRWC | Not started | 250001 | 500000 | Partially funded | Instream habitat restoration, stream bank stabilization | yes | LW
Prosser Creek Basin | Carpenter Valley Watershed | Nevada | CA | Assessment | Private |  |  | Not started | 0 | 50000 | Not funded | Should this be separate from Proseer Creek Assessment?
Prosser Creek Basin | Euer Valley Watershed Assessment | Nevada | CA | Assessment | Private | Tahoe Donner |  | Not started | 0 | 50000 | Not funded
Prosser Creek Basin | Prosser Creek Bridge Scour repair | Nevada | CA | Design | Public | Caltrans DOT |  | Partially Completed |  |  | Fully funded | In the environmental phase; Repair scour at the piers and abutments of the highway 89 bridge at Prosser Creek
Prosser Creek Basin | Prosser Creek Bridge Scour repair | Nevada | CA | Implementation | Public | Caltrans DOT |  | Not started
Prosser Creek Basin | Prosser Creek Trailhead | Nevada | CA | Design | Public | USFS |  | Completed | 50001 | 100000 | Fully funded | Current conditions: A user-created parking area accessing the Commemorative Overland Emigrant Trail at Prosser Creek has become extremely popular. This parking area is far below Forest Service standards, is unsafe (no Highway 89 encroachment), and it creates servere erosion control problems for Prosser Creek. Project description: Obliterate existing parking area next to highway. Replace with a Forest Service approved parking area off of Hobart Mills Rd. Create a linkage trail (~1/4 mi) to connect to existing trail. Install informational kiosk.
Prosser Creek Basin | Prosser Creek Trailhead | Nevada | CA | Implementation | Public | USFS |  | Not started |  |  | Not funded |  | yes
Prosser Creek Basin | Prosser Creek Watershed | Nevada | CA | Assessment | Both | Multiple |  | Partially Completed | 50001 | 100000 | Partially funded |  |  | LW
Prosser Creek Basin | Prosser Lakeside Campground Road Obliteration and Erosion Control | Nevada | CA | Design | Public | USFS | USFS | Completed |  |  | Fully funded | CHECK ON DETAILS WITH BC - Lakeside Campground is currently a large compacted area with numerous roads that go to the same place. This is causing erosion into the reservoir and takes away from the recreational experience. To reduce erosion into the reservoir, reduce compaction, restore vegetation to denuded areas, and improve the recreational experience several thousand feet of road can be obliterated and revegetated and prefered routes will be delineated. Lakeside is very popular with Off Highway Vehicles, and directional barriers would reduce damage to natural resources and prevent further compaction and user created routes. Prosser Creek drains into the main stem of the Truckee. |  | LW
Prosser Creek Basin | Prosser Lakeside Campground Road Obliteration and Erosion Control | Nevada | CA | Implementation | Public | USFS | USFS | Partially Completed |  |  | Partially funded | CHECK PROJECT DETAILS WITH BC - Lakeside Campground is currently a large compacted area with numerous roads that go to the same place. This is causing erosion into the reservoir and takes away from the recreational experience. To reduce erosion into the reservoir, reduce compaction, restore vegetation to denuded areas, and improve the recreational experience several thousand feet of road can be obliterated and revegetated and prefered routes will be delineated. Lakeside is very popular with Off Highway Vehicles, and directional barriers would reduce damage to natural resources and prevent further compaction and user created routes. Prosser Creek drains into the main stem of the Truckee. | yes | LW
Sagehen Creek Basin | Embankment repair at Sagehen Creek | Nevada | CA | Implementation | Public | Caltrans DOT |  | Completed |  |  | Fully funded | Caltrans repaired a small slope failure where Sagehen Creek crosses under highway 89. The repair included root wads and willow plantings
Sagehen Creek Basin | Fen Restoration (need fen name) | Nevada | CA | Design | Public | USFS | USFS | Completed |  |  | Fully funded | RANDY W TO PROVIDE COST - The lower slope of a fen has been disected by the 11-05 road. This road will be decomissioned and the fen restored. The section of the road which passes through the bottom end of a fen (300 feet) and its associated culvert system would be removed and full restoration measures improving the hydrology through the fen will improve approximately three acres of hydrology surrounding the fen. |  | LW
Sagehen Creek Basin | Fen Restoration (need fen name) | Nevada | CA | Implementation | Public | USFS |  | Partially Completed |  |  | Not funded | RANDY W TO PROVIDE COST ESTIMATE | yes | LW
Sagehen Creek Basin | Lower Sagehen Creek Restore Stream Bank | Sierra | CA | Design | Public | USFS |  | Not started | 0 | 50000 | Not funded | The lower section of Sagehen Creek is degrade from a variety of impacts and the banks are unstable and eroding. The current project is to design a projects to stabilize the banks.
Sagehen Creek Basin | Sagehen Basin Old Forest Sensitive Species Habitat Restoration | Nevada | CA | Design | Public | USFS | USFS | Completed | 250001 | 500000 | Fully funded | Because of fire suppression, the majority of the Sagehen Basin is comprised of thick, homogenous stands of trees. Very few wildlife species take advantage of these unnatural conditions and none thrive when those conditions are so ubiquitous. The Sagehen Basin Habitat project aims to introduce stand variability through hand vegetation treatments while enhancing forest decadence by creating snags. Further, existing pockets of mature cover and decadence will be designated and maintained. Finally, all of the designations and treatments will vary in intensities depending on their topographic position on the landscape. Successful implementation of this project will not only safeguard appropriate amounts of decadence and cover for nesting and denning habitats of old forest sensitive species, but will also create an abundance of close proximity foraging habitat these species require. |  | LW
Sagehen Creek Basin | Sagehen Basin Old Forest Sensitive Species Habitat Restoration | Nevada | CA | Implementation | Public | USFS |  | Not started |  |  | Not funded | SCOTT CONWAY TO PROVIDE COST |  | LW
Sagehen Creek Basin | Sagehen Creek Trail Relocation | Sierra | CA | Design | Public | USFS |  | Partially Completed | 250001 | 500000 | Partially funded | The existing trail goes from Hwy 89N to Stampede Reservoir. The trail was developed from public use and was not designed as an official trail. There are several sections of trail that are too steep, have erosion problems, or are too close to the creek. This project proposes to design and implement a new trail to that meet TNF standards and guidlines and minimizes erosion and sediment to the creek while enhancing the public recreational experience in the area.
Silver Creek Basin | Silver Creek Watershed | Placer | CA | Assessment | Both |  |  | Not started | 0 | 50000 | Not funded
Squaw Creek Basin | Lower Squaw Creek Restoration Project | Placer | CA | Design | Private | Placer County | Numerous | Partially Completed | 250001 | 500000 | Partially funded | Seeking funding to complete design & CEQA. Implementation (construction) will follow in stages. | No | ed sullivan, 2013
Tahoe City Basin | Fanny Bridge | Placer | CA | Design | Both | TTD/CFL/Caltrans |  | Partially Completed |  |  | Fully funded | Improve the ooperations and traffic movements at 89/28 in Tahoe City - alternatives may include a new crossing over the Truckee River. Operational Improvements - Realignment
Tahoe City Basin | Fanny Bridge | Placer | CA | Implementation | Both | TTD/CFL/Caltrans |  | Not started |  |  | Fully funded
Tahoe City Basin | Lakeside Roadway & Drainage Improvements | Placer | CA | Implementation | Public | Caltrans DOT |  | Partially Completed |  |  | Fully funded | Rehabilitate the roadway, update the drainage and improve stormwater treatment.
Tahoe City Basin | Route 28 to Squaw Valley Roadway & Drainage Improvements | Placer | CA | Implementation | Public | Caltrans DOT |  | Completed |  |  | Fully funded | Rehabilitate the roadway, update the drainage and improve stormwater treatment. part of the Environmental Improvement Program
Tahoe City Basin | Tahoe City Watershed | Placer | CA | Assessment | Both | Multiple |  | Completed | 0 | 50000 | Fully funded | Included in Truckee River Cooridor Access Plan
Trout Creek Basin | Stream Restoration in Town | Nevada | CA | Design | Public | Town of Truckee | Town of Truckee | Completed | 250001 | 500000 | Fully funded |  |  | LW/BB
Trout Creek Basin | Stream Restoration in Town | Nevada | CA | Implementation | Public | Town of Truckee | Town of Truckee | Partially Completed | 1000001 | 2000000 | Partially funded | Reach 1 partially completed, reach 2 and 3 completed. | yes | LW/BB
Trout Creek Basin | Trout Creek Pocket Park | Nevada | CA | Design | Public | Town of Truckee | Town of Truckee, MAP | Partially Completed | 50001 | 100000 | Partially funded |  | maybe | LW/BB
Trout Creek Basin | Trout Creek Pocket Park | Nevada | CA | Implementation | Public | Town of Truckee | Town of Truckee, MAP | Not started |  |  | Not funded | BECKY BUCAR FOR COSTS (OR ALEXIS OLLAR) | yes | LW/BB
Truckee Town Corridor | Bridge piers at Donner Creek and Truckee River | Nevada | CA | Implementation | Both | Multiple | TRWC | Completed | 0 | 50000 | Fully funded |  | yes
Truckee Town Corridor | CA DFW River Front | Nevada | CA | Design | Public | Multiple |  | Not started |  |  | Not funded |  |  | LW
Truckee Town Corridor | Confluence of Donner Creek and Truckee River | Nevada | CA | Design | Both | Multiple |  | Partially Completed |  |  | Partially funded |  | yes
Truckee Town Corridor | East River St. LID/Stormwater | Nevada | CA | Design | Public | Town of Truckee | Town of Truckee | Not started | 250001 | 500000 | Not funded |  |  | LW/BB
Truckee Town Corridor | East River St. LID/Stormwater | Nevada | CA | Implementation | Public | Town of Truckee | Town of Truckee | Not started | 1000001 | 2000000 | Not funded |  |  | LW/BB
Truckee Town Corridor | RFL | Nevada | CA | Implementation | Private |  |  | Partially Completed |  |  | Partially funded
Truckee Town Corridor | Stormdrain Marker Installation | Nevada | CA | Implementation | Public | Town of Truckee |  | Partially Completed |  |  | Partially funded |  | yes
Truckee Town Corridor | Stormwater Management | Nevada | CA | Implementation | Public | Placer County |  | Partially Completed |  |  | Partially funded
Truckee Town Corridor | Truckee Wetlands Restoration | Nevada | CA | Design | Public | Multiple |  | Partially Completed |  |  | Partially funded |  | maybe
Truckee Town Corridor | West River St. LID/Stormwater | Nevada | CA | Design | Public | Town of Truckee | Town of Truckee | Not started | 250001 | 500000 | Not funded |  |  | LW/BB
Truckee Town Corridor | West River St. LID/Stormwater | Nevada | CA | Implementation | Public | Town of Truckee | Town of Truckee | Not started | 1000001 | 2000000 | Not funded |  |  | LW/BB
Truckee Town Corridor | BMP/LID Certification Training Program for Truckee River Watershed | Multiple | CA | Design | Public | Multiple |  | Not started |  |  | Not funded |  |  | LW
Truckee Town Corridor | Mousehole | Nevada | CA | Design | Public | Caltrans, Town of Truckee | Caltrans, Town of Truckee | Partially Completed |  |  | Fully funded | Install a pedestrian undercrossing beneath the railroad
Truckee Town Corridor | Mousehole | Nevada | CA | Implementation | Public | Caltrans, Town of Truckee | Caltrans, Town of Truckee | Not started
Truckee Town Corridor | Relocate the Floriston Sandhouse | Nevada | CA | Design | Public | Caltrans DOT |  | Partially Completed |  |  | Fully funded | Caltrans is reviewing several Caltrans owned locations for the new Floriston sandhouse - removal of the old facility wil be a separate action following construction of the new sandhouse; In the alternatives development phase
Truckee Town Corridor | Relocate the Floriston Sandhouse | Nevada | CA | Implementation | Public | Caltrans DOT |  | Not started
Upper Little Truckee Basin | Assessment below LTR Diversion | Sierra | CA | Assessment | Public | USFS |  | Partially Completed | 50001 | 250000 | Partially funded | This project is for projects that will be identified in the assessment of the Little Truckee River below the Perazzo Meadow system at the diversion to Sierra Valley and Stampede Reservoir. The assessment may identify potential projects to improve the stream/meadow areas within this reach of the Little Truckee River.The assessment of this section of the Little Truckee River has been funded by a Forest Service RAC grant and is in progress. The assessment should be completed by the 2014 field season. Watershed/stream/meadow projects identified by this assessment would then need NEPA/CEQA analysis and then be ready for implementation potentially by 2015. |  | LW
Upper Little Truckee Basin | Bickford Meadows Watershed Assessment | Sierra | CA | Assessment | Private | TDLT |  | Not started | 0 | 50000 | Not funded
Upper Little Truckee Basin | Hwy 89 Little Truckee River Bridge | Sierra | CA | Design | Public | USFS |  | Not started | 1000001 | 2000000 | Not funded
Upper Little Truckee Basin | Lacey Meadow | Sierra | CA | Acquistion | Public | TDLT, USFS | TDLT | Completed | 2000001 | + | Fully funded | see John Svahn |  | LW/JS
Upper Little Truckee Basin | Lacey Meadow | Sierra | CA | Assessment | Public | TDLT, USFS | TRWC | Completed | 0 | 50000 | Fully funded |  |  | LW/JS
Upper Little Truckee Basin | Lacey Meadow Drainage Renaturalization | Sierra | CA | Design | Public | TDLT |  | Not started | 0 | 50000 | Not funded | get from assessment |  | LW
Upper Little Truckee Basin | Lacey Meadow Drainage Renaturalization | Sierra | CA | Implementation | Public | TDLT |  | Not started | 250001 | 500000 | Not funded | get from assessment | yes | LW
Upper Little Truckee Basin | Lacey Meadow Forest Management Plan | Sierra | CA | Design | Public | TDLT |  | Not started | 0 | 50000 | Not funded | get from assessment |  | LW
Upper Little Truckee Basin | Lacey Meadow Forest Management Plan | Sierra | CA | Implementation | Public | TDLT |  | Not started | 0 | 50000 | Not funded | get from assessment; reassess at 10 years |  | LW
Upper Little Truckee Basin | Lacey Meadow Forest Management Plan | Sierra | CA | Post-Project Monitoring | Public | TDLT |  | Not started | 0 | 50000 | Not funded | get from assessment; reassess at 10 years |  | LW
Upper Little Truckee Basin | Lacey Meadow Grazing Management Plan | Sierra | CA | Design | Public | TDLT |  | Not started | 0 | 50000 | Not funded | get from assessment |  | LW
Upper Little Truckee Basin | Lacey Meadow Grazing Management Plan | Sierra | CA | Post-Project Monitoring | Public | TDLT |  | Not started | 0 | 50000 | Not funded | get from assessment; reassess at 10 years |  | LW
Upper Little Truckee Basin | Lacey Meadow Grazing Management Plan - Long Term | Sierra | CA | Implementation | Public | TDLT |  | Not started | 0 | 50000 | Not funded | get from assessment; reassess at 10 years |  | LW
Upper Little Truckee Basin | Lacey Meadow Grazing Management Plan - Short Term | Sierra | CA | Implementation | Public | TDLT |  | Not started | 0 | 50000 | Not funded | get from assessment; reassess at 10 years |  | LW
Upper Little Truckee Basin | Lacey Meadow Lake Level Management and Mitigation | Sierra | CA | Design | Public | TDLT |  | Not started | 0 | 50000 | Not funded | get from assessment |  | LW
Upper Little Truckee Basin | Lacey Meadow Lake Level Management and Mitigation | Sierra | CA | Implementation | Public | TDLT |  | Not started | 0 | 50000 | Not funded | get from assessment | yes | LW
Upper Little Truckee Basin | Lacey Meadow Lower Meadow Restoration | Sierra | CA | Design | Public | TDLT |  | Not started | 0 | 50000 | Not funded | get from assessment |  | LW
Upper Little Truckee Basin | Lacey Meadow Lower Meadow Restoration | Sierra | CA | Design | Public | TDLT |  | Not started | 0 | 50000 | Not funded | get from assessment |  | LW
Upper Little Truckee Basin | Lacey Meadow Lower Meadow Restoration | Sierra | CA | Implementation | Public | TDLT |  | Not started | 50001 | 100000 | Not funded | get from assessment | yes | LW
Upper Little Truckee Basin | Lacey Meadow Recreation Management Plan | Sierra | CA | Design | Public | TDLT |  | Not started | 0 | 50000 | Not funded | get from assessment |  | LW
Upper Little Truckee Basin | Lacey Meadow Recreation Management Plan | Sierra | CA | Implementation | Public | TDLT |  | Not started | 0 | 50000 | Not funded | get from assessment; reassess at 10 years |  | LW
Upper Little Truckee Basin | Lacey Meadow Recreation Management Plan | Sierra | CA | Post-Project Monitoring | Public | TDLT |  | Not started | 0 | 50000 | Not funded | get from assessment; reassess at 10 years |  | LW
Upper Little Truckee Basin | Lacey Meadow Upper Meadow Restoration | Sierra | CA | Design | Public | TDLT |  | Not started | 0 | 50000 | Not funded | get from assessment |  | LW
Upper Little Truckee Basin | Lacey Meadow Upper Meadow Restoration | Sierra | CA | Implementation | Public | TDLT |  | Not started | 50001 | 100000 | Not funded | get from assessment | yes | LW
Upper Little Truckee Basin | LCT Reintroduction | Nevada | CA | Design | Public | USFS, TDLT USFWS |  | Not started | 500001 | 100000 | Not funded | NEPA, fish barrier design and non-native eradication planning work |  | LW, RM, DL
Upper Little Truckee Basin | LCT Reintroduction | Nevada | CA | Implementation | Public | USFS, TDLT USFWS |  | Not started | 50001 | + | Not funded | see Dave Lass? |  | LW, RM, DL
Upper Little Truckee Basin | Outback Watershed Improvement Project | Sierra | CA | Design | Public | USFS | USFS | Completed |  |  | Fully funded | QUENTIN OR RANDY W TO PROVIDE COSTS |  | LW
Upper Little Truckee Basin | Outback Watershed Improvement Project | Sierra | CA | Implementation | Public | USFS | USFS | Partially Completed |  |  | Partially funded | This project has seveal watershed improvement components related to the Outback Aspen Restoration Project. The project includes reclaiming a historic roadbed that intercepts groundwater along most of its length, pulling a culvert in a perennial stream segment (unit (7354071), culvert replacement for aquatic passage on the 301-75 road, closing and restoring hydrologic connectivity on road 7-10-10, and headcut treatment to stabilize a meadow. |  | LW
Upper Little Truckee Basin | Perazzo Meadows | Sierra | CA | Implementation | Public | USFS | TRWC, USFS | Partially Completed | 500001 | 1000000 | Partially funded |  | yes | QY
Upper Little Truckee Basin | Phoenix Project | Sierra | CA | Implementation | Public | USFS |  | Not started | 0 | 50000 | Not funded |  |  | LW
Upper Little Truckee Basin | Phoenix Project | Sierra | CA | Design | Public | USFS | USFS | Completed | 0 | 50000 | Fully funded | The proposed actions asociated with the Phoenix Project include various road closures and decommissioning and drainage improvements to restore hydrologic conectivity within the Independence Creek Watershed. Improve hydrologic conectivity of 11 miles of road, Gate and restore hydrologic conectivity on several roads. Decommision .5 miles of road. |  | LW
Upper Little Truckee Basin | Sierra 89 Paired Wildlife Crossing Structures | Sierra | CA | Implementation | Public | Caltrans DOT |  | Not started |  |  | Fully funded | Construct 2 wildlife undercrossings on the Sierra County side of Sagehen grade. Fencing to be included in this phase. 2015
Upper Little Truckee Basin | Sierra 89 Wildlife Undercrossing Phase 1 | Sierra | CA | Implementation | Public | Caltrans DOT |  | Completed |  |  | Fully funded | In conjunction with the Sierra 89 Stewardship Team and Sierra County the project scope was to build a wildlife undercrossing at a single location - Kyburz Flat was selected after a corridor analysis
Upper Little Truckee Basin | Sierra 89 Wildlife Undercrossing Phase 2 | Sierra | CA | Implementation | Public | Caltrans DOT |  | Partially Completed |  |  | Fully funded | Phase 2 of the undercrossing project inlcudes fencing and rock as a highway barrier for wildlife. Also included are jumpouts and end treatments.
Upper Little Truckee Basin | Underground Water storage | Sierra | CA | Assessment | Both | USFS |  | Not started | 0 | 50000 | Not funded | SHOULD THIS BE HERE??
Upper Little Truckee Basin | Upper Little Truckee River Braiding | Sierra | CA | Design | Both | USFS |  | Not started |  |  | Not funded
Upper Little Truckee Basin | Upper Little Truckee Watershed | Sierra | CA | Assessment | Private | TDLT |  | Partially Completed | 50001 | 500000 | Partially funded | Lacey Creek watershed is currently owned by the Truckee Donner Land Trust. The area is surrounded by FS lands and is upstream from the Perazzo Meadows area where meadow restoration has been completed in 2009 and 2010. Assessment of the Lacey Creek watershed. The assessment may identify potential projects to improve the stream/meadow areas within this reach of the headwaters of the Little Truckee River
Upper Little Truckee Basin | Willow Flycatcher Post-Monitoring | Sierra | CA | Post-Project Monitoring | Public | USFS | UCSF, USFS |  |  |  |  | need costs from Randy Westmoreland |  | RM, LW

## Definitions
Project Name | Approx 3-6 words
Description | Approx 50 words
Project Type | Choose primary (implementation includes monitoring) | Acquistion
Assessment
|  | Design | includes CEQA/NEPA, bidding package, tech studies, concept
|  | Implementation | pre-project monitoring, permitting, construction, construction monitoring, as-builts
Post-Project Monitoring
County | Choose one | Nevada
Placer
Sierra
Washoe
Multiple
State | Choose one | CA
NV
Project Status | Choose one | Not started
Partially Completed
Completed
Total Cost Est Low | total cost for status. If completed $$ are actual, if other status = estimate | 0
50001
100001
250001
500001
1000001
2000001
Total Cost Est High | total cost for status. If completed $$ are actual, if other status = estimate | 50000
100000
250000
500000
1000000
2000000
+
1000000
Funding Status | Choose one | Not funded
Partially funded
Fully funded
Property Type | Choose one | Public
Private
Both
Landowner/Mgr | List one: "Multiple", Agency Name, Landowner Name (not contact info, don't want to maintain it in this list)
Truckee River Day project | Choose one | Yes
No
Sub-basin | Choose one | Entire Watershed
Alder Creek Basin
Bear Creek Basin
Big Chief Corridor
Boca Complex
Bronco Creek Basin
Cabin Creek Basin
Coldstream Canyon Basin
Davies-Merrill Creek Basin
Deep Creek Basin
Deer Creek Basin
Donner Lake Basin
Glenshire / Union Valley Basin
Gray Creek Basin
I-80 Corridor
Independence Lake Basin
Juniper Creek Basin
Martis Creek Basin
Mystic Canyon Basin
Pole Creek Basin
Prosser Creek Basin
Sagehen Creek Basin
Silver Creek Basin
Squaw Creek Basin
Tahoe City Basin
Trout Creek Basin
Truckee Town Corridor
Upper Little Truckee Basin
Financial Partner | Name of Agency or Org that has received funding for the project
Community Work Day | Assumes potential, past, current; TU, WW, TRD, TTF, TDLT, Sierra River Cleanup, Public Lands Day, etc.
Projects Not on List | In some watershed assessments, some project are identified but determined not feasible; therefore, these are not included on the list. | Note to self - don't need to share unless asked to avoid confusion
Projects Term | If program and expected to continue for numberous years; # year budgeted is stated in the definition section; i.e. AIS 75K/yr for 10 years

## P&A Format for handout
Sub Basin | Project Name | Project Type | Property Type | Landowner /Mgr | Financial Partners | Status | Cost Low | Cost High | Funding Status
Alder Creek Basin | Alder Creek Watershed | Assessment | Both | Multiple |  | Not started | 0 | 50000 | Not funded
Alder Creek Basin | Emigrant Trail | Design | Public | USFS |  | Not started |  |  | Not funded
Alder Creek Basin | Prosser Lake View- Emigrant Trail | Implementation | Public | USFS |  | Not started |  |  | Not funded
Alder Creek Basin | Prosser Lake View- Emigrant Trail | Design | Public | USFS |  | Not started |  |  | Not funded
Alder Creek Basin | Trail Crossings and Trail Maintenance (Alder Rd Reach) | Design | Public | USFS |  | Not started | 0 | 50000 | Not funded
Alder Creek Basin | Trail Crossings and Trail Maintenance (Alder Rd Reach) | Implementation | Public | USFS |  | Not started |  |  | Not funded
Alder Creek Basin | Upper Commemorative Overland Emigrant Trail Re-Routing | Design | Public | USFS |  | Not started | 0 | 50000 | Not funded
Bear Creek Basin | Alpine Meadows Ski Area Erosion | Design | Both | Alpine Meadows Squaw Valley |  | Not started | 0 | 50000 | Not funded
Bear Creek Basin | Bear Creek Watershed | Assessment | Both | Alpine Meadows, HOA, Placer County, USFS |  | Not started | 0 | 50000 | Not funded
Bear Creek Basin | Bear Creek Watershed | Assessment | Both | Multiple |  | Not started | 0 | 50000 | Not funded
Big Chief Corridor | Alpine Meadows Bridge Replacement |  |  |  | Caltrans, Placer County Co
Big Chief Corridor | First 4 Mile Restoration | Design | Public | USFS, TCPUD | TCPUD, TRWC, Placer Co | Partially Completed | 50001 | 100000 | Fully funded
Big Chief Corridor | First 4 Mile Restoration | Implementation | Public | USFS, TCPUD | TCPUD, TRWC | Not started | 100001 | 250000 | Partially funded
Big Chief Corridor | Truckee River Access Plan | Assessment | Public | Placer County | Placer CO | Completed | 0 | 50000 | Fully funded
Big Chief Corridor | Truckee River Corridor Access Plan | Assessment | Public | Numerous | Resort Assoc and Placer County | Partially Completed | 250001 | 500000 | Fully funded
Boca Complex | Boca Complex Watershed | Assessment | Public | USFS |  | Partially Completed | 0 | 50000 | Partially funded
Boca Complex | Boca-Stampede Noxious Weed Management | Design | Public | USFS | USFS | Completed | 0 | 50000 | Fully funded
Boca Complex | Boca-Stampede Noxious Weed Management | Implementation | Public | USFS | USFS, TRWC, SIERRA CO | Partially Completed | 100001 | 250000 | Partially funded
Boca Complex | Dry Creek Watershed | Assessment | Both | USFS | TRWC, USFS | Completed | 0 | 50000 | Fully funded
Boca Complex | Dry Creek Watershed - Main Channel | Design | Public | USFS |  | Not started | 0 | 50000 | Not funded
Boca Complex | Dry Creek Watershed - Main Channel | Implementation | Public | USFS |  | Not started | 0 | 50000 | Not funded
Boca Complex | Dry Creek Watershed - Tributary 16 | Design | Public | USFS |  | Not started | 0 | 50000 | Not funded
Boca Complex | Dry Creek Watershed - Tributary 16 | Implementation | Public | USFS |  | Not started | 0 | 50000 | Not funded
Boca Complex | Dry Creek Watershed - Tributary 1A | Design | Public | USFS |  | Not started | 0 | 50000 | Not funded
Boca Complex | Dry Creek Watershed - Tributary 1A | Implementation | Public | USFS |  | Not started | 0 | 50000 | Not funded
Boca Complex | Dry Creek Watershed - Tributary 21 | Design | Public | USFS |  | Not started | 0 | 50000 | Not funded
Boca Complex | Dry Creek Watershed - Tributary 21 | Implementation | Public | USFS |  | Not started | 0 | 50000 | Not funded
Boca Complex | Hoke Valley Watershed | Assessment | Public | USFS |  | Not started | 0 | 50000 | Not funded
Boca Complex | Kyburz Watershed | Assessment | Public | USFS |  | Not started | 50001 | 100000 | Not funded
Boca Complex | LTR Fish Habitat Restoration Project | Design | Public | USFS | USFS, TU | Partially Completed | 50001 | 100000 | Not funded
Boca Complex | LTR Fish Habitat Restoration Project | Implementation | Public | USFS | USFS, TU | Not started | 50001 | 100000 | Not funded
Boca Complex | Transition Road Decommisioning | Design | Public | USFS |  | Completed | 0 | 50000 | Fully funded
Boca Complex | Transition Road Decommisioning | Implementation | Public | USFS |  | Not started |  |  | Not funded
Bronco Creek Basin | Bronco Creek Watershed | Assessment | Public | USFS |  | Completed | 0 | 50000 | Fully funded
Cabin Creek Basin | Cabin Creek Watershed | Assessment | Both | Multiple |  | Not started | 0 | 50000 | Not funded
Coldstream Canyon Basin | Coldstream Canyon | Assessment | Public | Multiple | TRWC | Completed | 0 | 100000 | Not funded
Coldstream Canyon Basin | Coldstream Canyon Floodplain/Lower Alluvial Fan - CDPR | Design | Public | CDPR | TRWC, CDPR | Completed | 100001 | 250000 | Fully funded
Coldstream Canyon Basin | Coldstream Canyon Floodplain/Lower Alluvial Fan - CDPR | Implementation | Public | CDPR | TRWC, CDPR | Completed | 250001 | 500000 | Fully funded
Coldstream Canyon Basin | Coldstream Canyon Floodplain/Lower Alluvial Fan - CDPR | Post-Project Monitoring | Public | CDPR | TRWC, CDPR | Partially Completed | 0 | 50000 | Fully funded
Coldstream Canyon Basin | Coldstream Canyon Floodplain/Lower Alluvial Fan - Private | Design | Private | Private |  | Partially Completed | 0 | 50000 | Partially funded
Coldstream Canyon Basin | Coldstream Canyon Floodplain/Lower Alluvial Fan - Private | Implementation | Private | Private |  | Not started | 250001 | 500000 | Not funded
Coldstream Canyon Basin | Lower Valley Gravel Ponds | Design | Public | CDPR | TRWC, CDPR | Partially Completed | 0 | 50000 | Partially funded
Sub Basin | Project Name | Project Type | Property Type | Landowner /Mgr | Financial Partners | Status | Cost Low | Cost High | Funding Status
Coldstream Canyon Basin | Lower Valley Gravel Ponds | Implementation | Public | CDPR | TRWC, CDPR | Partially Completed | 100001 | 250000 | Partially funded
Coldstream Canyon Basin | Railroad Culvert Modification | Design | Both | Multiple |  | Not started | 50001 | 100000 | Not funded
Coldstream Canyon Basin | Railroad Culvert Modification | Implementation | Both | Multiple |  | Not started | 250001 | 250000 | Not funded
Coldstream Canyon Basin | Upland Areas | Design | Both | Multiple |  | Not started | 0 | 50000 | Not funded
Coldstream Canyon Basin | Upland Areas | Implementation | Both | Multiple |  | Not started | 50001 | 250000 | Not funded
Coldstream Canyon Basin | Upper Valley Woody Debris Placement | Design | Public | Multiple |  | Not started | 50001 | 100000 | Not funded
Coldstream Canyon Basin | Upper Valley Woody Debris Placement | Implementation | Public | Multiple |  | Not started | 0 | 50000 | Not funded
Davies-Merrill Creek Basin | Davies Meadow and Riparian, Phase 1 | Design | Public | USFS | USFS, TRWC | Completed | 50001 | 100000 | Fully funded
Davies-Merrill Creek Basin | Davies Meadow and Riparian, Phase 2 | Design | Both | USFS | USFS | Partially Completed |  |  | Partially funded
Davies-Merrill Creek Basin | Davies Meadow and Riparian, Phase 1 | Implementation | Public | USFS | USFS, TRWC | Completed | 100001 | 250000 | Fully funded
Davies-Merrill Creek Basin | Davies Meadow and Riparian, Phase 2 | Implementation | Both | USFS |  | Not started |  |  | Not funded
Davies-Merrill Creek Basin | Jammer Chair Stream and Aspen Restoration | Design | Public | USFS | USFS | Completed | 0 | 50000 | Fully funded
Davies-Merrill Creek Basin | Jammer Chair Stream and Aspen Restoration | Implementation | Public | USFS |  | Not started | 0 | 50000 | Not funded
Davies-Merrill Creek Basin | Jones Valley Meadow and Riparian Restoration | Design | Public | USFS | USFS, TRWC | Completed | 0 | 50000 | Fully funded
Davies-Merrill Creek Basin | Jones Valley Meadow and Riparian Restoration | Implementation | Public | USFS | USFS, TRWC | Completed | 0 | 50000 | Fully funded
Davies-Merrill Creek Basin | Sardine Valley | Acquistion | Both | Private |  | Not started | 250001 | 500000 | Not funded
Deep Creek Basin | Deep Creek Watershed | Assessment | Private |  |  | Not started | 0 | 50000 | Not funded
Deer Creek Basin | Deer Creek Watershed | Assessment | Public | USFS |  | Not started | 0 | 50000 | Not funded
Donner Lake Basin | Billy Mack Canyon | Acquistion | Private | TDLT |  | Completed | 1000001 | 2000000 | Fully funded
Donner Lake Basin | Billy Mack Canyon | Design | Public | TDLT |  | Not started | 1000001 | 2000000 | Not funded
Donner Lake Basin | Donner 1 Roadway & Drainage Improvement & Wetland Mitigation | Implementation | Public | Caltrans DOT |  | Completed |  |  | Fully funded
Donner Lake Basin | Donner 3 Roadway & Drainage Improvement & Wetland Mitigation | Implementation | Public | Caltrans DOT |  | Completed |  |  | Fully funded
Donner Lake Basin | Donner Creek at I-80 and Deerfield | Assessment | Both | Multiple |  | Not started | 0 | 50000 | Not funded
Donner Lake Basin | Donner Creek Watershed | Assessment | Both | Multiple |  | Not started | 0 | 50000 | Not funded
Donner Lake Basin | Donner Memorial State Park Expansion | Design | Public | CA State Parks |  | Not started |  |  | Not funded
Donner Lake Basin | Emigrant Canyon Road and Trails Watershed Rehabilitation | Design | Public | CA State Parks |  | Not started |  |  | Not funded
Donner Lake Basin | Johnson Canyon Restoration Site A | Implementation | Private | TDA |  | Not started | 50001 | 100000 | Not funded
Donner Lake Basin | Johnson Canyon Restoration Site B | Implementation | Private | TDA |  | Not started | 0 | 50000 | Not funded
Donner Lake Basin | Johnson Canyon Restoration Site C | Implementation | Both | TDA, USFS |  | Not started | 0 | 50000 | Not funded
Donner Lake Basin | Johnson Canyon Restoration Site D | Implementation | Both | TDA, TDLT |  | Not started | 0 | 50000 | Not funded
Donner Lake Basin | Johnson Canyon Restoration Site E - I | Implementation | Public | TDLT | TRWC | Partially Completed | 100001 | 250000 | Partially funded
Donner Lake Basin | Johnson Canyon Restoration Sites A-I | Design | Both | TDLT, USFS, TDA | TRWC | Partially Completed | 50001 | 100000 | Partially funded
Donner Lake Basin | Johnson Canyon Watershed | Acquisition | Public, Private | TDLT | TDLT | Completed | 1000001 | 2000000 | Fully funded
Donner Lake Basin | Johnson Canyon Watershed | Assessment | Both | TDLT, USFS, TDA | TRWC | Completed | 0 | 50000 | Fully funded
Donner Lake Basin | Lake View Canyon Road and Trails Watershed Rehabilitation | Design | Public | CA State Parks |  | Not started |  |  | Not funded
Donner Lake Basin | Shoreline Erosion (including piers) | Design | Both | Multiple |  | Not started | 50001 | 100000 | Not funded
Donner Lake Basin | Shoreline Erosion (including piers) | Implementation | Both | Multiple |  | Not started | 50001 | 100000 | Not funded
Donner Lake Basin | Summit Creek Restoration | Design | Public | CA State Parks, TDLT |  | Not started | 0 | 50000 | Not funded
Donner Lake Basin | Summit Creek Restoration | Implementation | Public | CA State Parks, TDLT |  | Not started | 100001 | 250000 | Not funded
Donner Lake Basin | Summit Creek Watershed | Assessment | Public | CA State Parks, TDLT | CA State Parks | Partially Completed | 0 | 50000 | Partially funded
Entire Watershed | Aquatic Invasive Species | Implementation | Both | Multiple |  | Partially Completed | 500001 | 1000000 | Partially funded
Entire Watershed | Dispersed Lakeshore Recreation Site Inventory and Rehabilitation | Assessment | Public | USFS |  | Not started | 0 | 50000
Entire Watershed | Highway Related Erosion And Restoration Projects | Implementation | Public | Multiple |  | Partially Completed |  |  | Partially funded
Entire Watershed | Post-Burn Noxious Weed Removal |  | Public | USFS
Entire Watershed | Post-Burn Revegetation |  | Public | USFS
Entire Watershed | Post-Burn Seeding with Native |  | Public | USFS
Entire Watershed | Roads Assessment | Assessment | Public | USFS |  | Partially Completed | 0 | 50000 | Partially funded
Entire Watershed | Sawtooth Trailhead Improvement | Design | Public | USFS |  | Not started | 0 | 50000 | Not funded
Sub Basin | Project Name | Project Type | Property Type | Landowner /Mgr | Financial Partners | Status | Cost Low | Cost High | Funding Status
Entire Watershed | Truckee River Recreation Access | Assessment | Public | USFS |  | Not started | 100001 | 250000 | Not funded
Entire Watershed | Waterbars - Post-burn (use burned trees) |  | Public | USFS
Glenshire / Union Valley Basin | Canyon Springs Trails erosion control | Design | Private | Canyon Springs LLC |  | Not started |  |  | Not funded
Glenshire / Union Valley Basin | Culvert Crossing at Glenshire Dr | Design | Public | Town of Truckee |  | Not started |  |  | Not funded
Gray Creek Basin | Conifer Regeneration | Design | Public | CDFW, USFS | USFS | Completed | 0 | 50000 | Fully funded
Gray Creek Basin | Conifer Regeneration | Implementation | Public | CDFW, USFS | USFS | Completed | 50001 | 100000 | Fully funded
Gray Creek Basin | Cottonwood and Aspen Regeneration | Design | Public | CDFW, USFS |  | Not started |  |  | Not funded
Gray Creek Basin | Cottonwood and Aspen Regeneration | Implementation | Public | CDFW, USFS |  | Not started |  |  | Not funded
Gray Creek Basin | Fish Passage | Design | Both | CDFW, USFS, private |  | Not started | 0 | 50000 | Not funded
Gray Creek Basin | Fish Passage | Implementation | Both | CDFW, USFS, private |  | Not started | 0 | 50000 | Not funded
Gray Creek Basin | Gray Creek Watershed | Acquistion | Public | USFS | TDLT, TRWC | Completed | 500001 | 1000000 | Fully funded
Gray Creek Basin | Gray Creek Watershed | Assessment | Both | Multiple | TRWC | Completed | 0 | 100000 | Fully funded
Gray Creek Basin | Logging Road and Skid Decommissioning | Design | Public | USFS | TRWC | Completed | 0 | 50000 | Fully funded
Gray Creek Basin | Logging Road and Skid Decommissioning | Implementation | Public | USFS | TRWC | Completed | 50001 | 100000 | Fully funded
Gray Creek Basin | Logging Road and Skid Decommissioning | Post-Project Monitoring | Public | USFS | TRWC | Completed | 0 | 50000 | Fully funded
Gray Creek Basin | Noxious Weed Control | Design | Both | CDFW, USFS, private |  | Not started | 0 | 50000 | Not funded
Gray Creek Basin | Noxious Weed Control | Implementation | Both | CDFW, USFS, private |  | Not started | 0 | 50000 | Not funded
I-80 Corridor | Boca-Floriston Roadway & Drainage Improvements | Implementation | Public | Caltrans DOT |  | Completed |  |  | Fully funded
I-80 Corridor | Boca-Floriston Roadway & Drainage Improvements | Implementation | Public | Caltrans DOT |  | Completed |  |  | Fully funded
I-80 Corridor | Hirschdale Bridge Replacement | Design |  |  | Caltrans, Nevada Co | Partially Completed
I-80 Corridor | I-80 Corridor Watershed | Assessment | Public | CDFW |  | Not started | 0 | 50000 | Not funded
I-80 Corridor | I-80 Corridor Watershed Noxious Weed Control | Design | Public | CDFW |  | Not started | 0 | 50000 | Not funded
I-80 Corridor | I-80 Corridor Watershed Noxious Weed Control | Implementation | Public | CDFW | SBC, Washoe County Dept. of Regional Parks and Open Space | Completed | 100001 | 250000 | Fully funded
Independence Lake Basin | Bridge replacement | Implementation | Public | TNC,Sierra Co | Sierra, TNC | Partially Completed |  |  | Fully funded
Independence Lake Basin | Delta and spawning grounds | Design | Public, Private | USFS | TNC, TRWC | Completed
Independence Lake Basin | Delta and spawning grounds | Implementation | Both | USFS | TNC, TRWC | Completed |  |  | Fully funded
Independence Lake Basin | Fish Barrier | Implementation | Public | TNC | TNC, TRWC | Completed |  |  | Fully funded
Independence Lake Basin | Independence Lake Bridge Replacement |  |  |  | Caltrans, Sierra Co
Independence Lake Basin | Independence Lake Trail | Design | Public | USFS, TNC |  | Partially Completed |  |  | Not funded
Independence Lake Basin | Independence Lake Trail | Implementation | Public | USFS |  | Not started
Independence Lake Basin | Independence Lake Watershed | Assessment | Both | Multiple |  | Not started | 0 | 50000 | Not funded
Independence Lake Basin | Independence Tributary Restoration | Assessment | Public | USFS |  | Completed | 0 | 50000 | Fully funded
Independence Lake Basin | Independence Tributary Restoration | Design | Public | USFS |  | Completed |  |  | Fully funded
Independence Lake Basin | Independence Tributary Restoration | Implementation | Public | USFS |  | Completed |  |  | Fully funded
Independence Lake Basin | Self-Reproducing LCT Management | Post-Project Monitoring | Public | USFS | USGS | Partially Completed | 0 | 50000 | Partially funded
Juniper Creek Basin | Juniper Creek Watershed | Assessment | Both | Multiple |  | Not started | 0 | 50000 | Not funded
Martis Creek Basin | Elizabeth Town | Design | Public | TDLT | TRWC, TDLT | Partially Completed | 0 | 50000 | Partially funded
Martis Creek Basin | Elizabeth Town | Implementation | Public | TDLT | TRWC, TDLT | Not started | 0 | 50000 | Not funded
Martis Creek Basin | Martis Creek Watershed | Assessment | Both | Multiple | TRWC | Completed | 50001 | 100000 | Fully funded
Martis Creek Basin | Martis WLA Ck Diversion Dam Removal | Implementation | Public | ACOE | ACOE | Not started | 50001 | 100000
Martis Creek Basin | Middle Martis Creek | Design | Public | Multiple | TRWC, TTAD | Partially Completed | 250001 | 500000 | Partially funded
Martis Creek Basin | Middle Martis Creek | Implementation | Public | Multiple | TRWC, TTAD, NCSD, CalTrans | Not started | 500001 | 1000000 | Not funded
Martis Creek Basin | Project 1 | Design |  |  |  | Not started | 0 | 50000 | Not funded
Martis Creek Basin | Project 1 | Implementation |  |  |  | Not started | 50001 | 100000 | Not funded
Martis Creek Basin | Project 10 | Design |  |  |  | Not started | 0 | 50000 | Not funded
Martis Creek Basin | Project 10 | Implementation |  |  |  | Not started | 50001 | 100000 | Not funded
Martis Creek Basin | Project 12 | Design |  |  |  | Not started | 100001 | 250000 | Not funded
Martis Creek Basin | Project 12 | Implementation |  |  |  | Not started | 500001 | 1000000 | Not funded
Martis Creek Basin | Project 13 | Design |  |  |  | Not started | 0 | 50000 | Not funded
Sub Basin | Project Name | Project Type | Property Type | Landowner /Mgr | Financial Partners | Status | Cost Low | Cost High | Funding Status
Martis Creek Basin | Project 13 | Implementation |  |  |  | Not started | 50001 | 100000 | Not funded
Martis Creek Basin | Project 14 | Design |  |  |  | Not started | 0 | 50000 | Not funded
Martis Creek Basin | Project 14 | Implementation |  |  |  | Not started | 50001 | 100000 | Not funded
Martis Creek Basin | Project 15 | Design |  |  |  | Not started | 0 | 50000 | Not funded
Martis Creek Basin | Project 15 | Implementation |  |  |  | Not started | 50001 | 100000 | Not funded
Martis Creek Basin | Project 16 | Design |  |  |  | Not started | 0 | 50000 | Not funded
Martis Creek Basin | Project 16 | Implementation |  |  |  | Not started | 50001 | 100000 | Not funded
Martis Creek Basin | Project 17 | Design |  |  |  | Not started | 0 | 50000 | Not funded
Martis Creek Basin | Project 17 | Implementation |  |  |  | Not started | 50001 | 100000 | Not funded
Martis Creek Basin | Project 2 | Design |  |  |  | Not started | 0 | 50000 | Not funded
Martis Creek Basin | Project 2 | Implementation |  |  |  | Not started | 50001 | 100000 | Not funded
Martis Creek Basin | Project 3 | Design |  |  |  | Not started | 0 | 50000 | Not funded
Martis Creek Basin | Project 3 | Implementation |  |  |  | Not started | 50001 | 100000 | Not funded
Martis Creek Basin | Project 4 | Design |  |  |  | Not started | 0 | 50000 | Not funded
Martis Creek Basin | Project 4 | Implementation |  |  |  | Not started | 50001 | 100000 | Not funded
Martis Creek Basin | Project 5 | Design |  |  |  | Not started | 0 | 50000 | Not funded
Martis Creek Basin | Project 5 | Implementation |  |  |  | Not started | 50001 | 100000 | Not funded
Martis Creek Basin | Project 6 | Design |  |  |  | Not started | 0 | 50000 | Not funded
Martis Creek Basin | Project 6 | Implementation |  |  |  | Not started | 50001 | 100000 | Not funded
Martis Creek Basin | Project 7 - dupe with E-Town? | Design |  |  |  | Not started |  |  | Not funded
Martis Creek Basin | Project 7 - dupe with E-Town? | Implementation |  |  |  | Not started |  |  | Not funded
Martis Creek Basin | Project 8 | Design |  |  |  | Not started | 0 | 50000 | Not funded
Martis Creek Basin | Project 8 | Implementation |  |  |  | Not started | 50001 | 100000 | Not funded
Martis Creek Basin | Project 9 | Design |  |  |  | Not started | 0 | 50000 | Not funded
Martis Creek Basin | Project 9 | Implementation |  |  |  | Not started | 50001 | 100000 | Not funded
Mystic Canyon Basin | Mystic Canyon Watershed | Assessment | Public | USFS |  | Not started | 0 | 50000 | Not funded
Pole Creek Basin | Pole Creek Watershed | Assessment | Public | USFS |  | Not started | 50001 | 100000 | Not funded
Prosser Creek Basin | Alder Drive Roundabout | Implementation | Public | Town of Truckee | Town of Truckee | Completed |  |  | Fully funded
Prosser Creek Basin | Backyard Trail – Prosser Lakeview | Design | Public | USFS |  | Partially Completed | 50001 | 100000 | Partially funded
Prosser Creek Basin | Backyard Trail – Prosser Lakeview | Implementation | Public | USFS |  | Not started | 50001 | 100000 | Not funded
Prosser Creek Basin | Below the Dam Fish Habitat Enhancement | Design | Public | USFS | USFS, TRWC | Completed |  |  | Fully funded
Prosser Creek Basin | Below the Dam Fish Habitat Enhancement | Implementation | Public | USFS | USFS, TRWC | Not started | 250001 | 500000 | Partially funded
Prosser Creek Basin | Carpenter Valley Watershed | Assessment | Private |  |  | Not started | 0 | 50000 | Not funded
Prosser Creek Basin | Euer Valley Watershed Assessment | Assessment | Private | Tahoe Donner |  | Not started | 0 | 50000 | Not funded
Prosser Creek Basin | Prosser Creek Bridge Scour repair | Design | Public | Caltrans DOT |  | Partially Completed |  |  | Fully funded
Prosser Creek Basin | Prosser Creek Bridge Scour repair | Implementation | Public | Caltrans DOT |  | Not started
Prosser Creek Basin | Prosser Creek Trailhead | Design | Public | USFS |  | Completed | 50001 | 100000 | Fully funded
Prosser Creek Basin | Prosser Creek Trailhead | Implementation | Public | USFS |  | Not started |  |  | Not funded
Prosser Creek Basin | Prosser Creek Watershed | Assessment | Both | Multiple |  | Partially Completed | 50001 | 100000 | Partially funded
Prosser Creek Basin | Prosser Lakeside Campground Road Obliteration and Erosion Control | Design | Public | USFS | USFS | Completed |  |  | Fully funded
Prosser Creek Basin | Prosser Lakeside Campground Road Obliteration and Erosion Control | Implementation | Public | USFS | USFS | Partially Completed |  |  | Partially funded
Sagehen Creek Basin | Embankment repair at Sagehen Creek | Implementation | Public | Caltrans DOT |  | Completed |  |  | Fully funded
Sagehen Creek Basin | Fen Restoration (need fen name) | Design | Public | USFS | USFS | Completed |  |  | Fully funded
Sagehen Creek Basin | Fen Restoration (need fen name) | Implementation | Public | USFS |  | Partially Completed |  |  | Not funded
Sagehen Creek Basin | Lower Sagehen Creek Restore Stream Bank | Design | Public | USFS |  | Not started | 0 | 50000 | Not funded
Sagehen Creek Basin | Sagehen Basin Old Forest Sensitive Species Habitat Restoration | Design | Public | USFS | USFS | Completed | 250001 | 500000 | Fully funded
Sagehen Creek Basin | Sagehen Basin Old Forest Sensitive Species Habitat Restoration | Implementation | Public | USFS |  | Not started |  |  | Not funded
Sagehen Creek Basin | Sagehen Creek Trail Relocation | Design | Public | USFS |  | Partially Completed | 250001 | 500000 | Partially funded
Silver Creek Basin | Silver Creek Watershed | Assessment | Both |  |  | Not started | 0 | 50000 | Not funded
Squaw Creek Basin | Lower Squaw Creek Restoration Project | Design | Private | Placer County | Numerous | Partially Completed | 250001 | 500000 | Partially funded
Tahoe City Basin | Fanny Bridge | Design | Both | TTD/CFL/Caltrans |  | Partially Completed |  |  | Fully funded
Tahoe City Basin | Fanny Bridge | Implementation | Both | TTD/CFL/Caltrans |  | Not started |  |  | Fully funded
Sub Basin | Project Name | Project Type | Property Type | Landowner /Mgr | Financial Partners | Status | Cost Low | Cost High | Funding Status
Tahoe City Basin | Lakeside Roadway & Drainage Improvements | Implementation | Public | Caltrans DOT |  | Partially Completed |  |  | Fully funded
Tahoe City Basin | Route 28 to Squaw Valley Roadway & Drainage Improvements | Implementation | Public | Caltrans DOT |  | Completed |  |  | Fully funded
Tahoe City Basin | Tahoe City Watershed | Assessment | Both | Multiple |  | Completed | 0 | 50000 | Fully funded
Trout Creek Basin | Stream Restoration in Town | Design | Public | Town of Truckee | Town of Truckee | Completed | 250001 | 500000 | Fully funded
Trout Creek Basin | Stream Restoration in Town | Implementation | Public | Town of Truckee | Town of Truckee | Partially Completed | 1000001 | 2000000 | Partially funded
Trout Creek Basin | Trout Creek Pocket Park | Design | Public | Town of Truckee | Town of Truckee, MAP | Partially Completed | 50001 | 100000 | Partially funded
Trout Creek Basin | Trout Creek Pocket Park | Implementation | Public | Town of Truckee | Town of Truckee, MAP | Not started |  |  | Not funded
Truckee Town Corridor | Bridge piers at Donner Creek and Truckee River | Implementation | Both | Multiple | TRWC | Completed | 0 | 50000 | Fully funded
Truckee Town Corridor | CA DFW River Front | Design | Public | Multiple |  | Not started |  |  | Not funded
Truckee Town Corridor | Confluence of Donner Creek and Truckee River | Design | Both | Multiple |  | Partially Completed |  |  | Partially funded
Truckee Town Corridor | East River St. LID/Stormwater | Design | Public | Town of Truckee | Town of Truckee | Not started | 250001 | 500000 | Not funded
Truckee Town Corridor | East River St. LID/Stormwater | Implementation | Public | Town of Truckee | Town of Truckee | Not started | 1000001 | 2000000 | Not funded
Truckee Town Corridor | RFL | Implementation | Private |  |  | Partially Completed |  |  | Partially funded
Truckee Town Corridor | Stormdrain Marker Installation | Implementation | Public | Town of Truckee |  | Partially Completed |  |  | Partially funded
Truckee Town Corridor | Stormwater Management | Implementation | Public | Placer County |  | Partially Completed |  |  | Partially funded
Truckee Town Corridor | Truckee Wetlands Restoration | Design | Public | Multiple |  | Partially Completed |  |  | Partially funded
Truckee Town Corridor | West River St. LID/Stormwater | Design | Public | Town of Truckee | Town of Truckee | Not started | 250001 | 500000 | Not funded
Truckee Town Corridor | West River St. LID/Stormwater | Implementation | Public | Town of Truckee | Town of Truckee | Not started | 1000001 | 2000000 | Not funded
Truckee Town Corridor | BMP/LID Certification Training Program for Truckee River Watershed | Design | Public | Multiple |  | Not started |  |  | Not funded
Truckee Town Corridor | Mousehole | Design | Public | Caltrans, Town of Truckee | Caltrans, Town of Truckee | Partially Completed |  |  | Fully funded
Truckee Town Corridor | Mousehole | Implementation | Public | Caltrans, Town of Truckee | Caltrans, Town of Truckee | Not started
Truckee Town Corridor | Relocate the Floriston Sandhouse | Design | Public | Caltrans DOT |  | Partially Completed |  |  | Fully funded
Truckee Town Corridor | Relocate the Floriston Sandhouse | Implementation | Public | Caltrans DOT |  | Not started
Upper Little Truckee Basin | Assessment below LTR Diversion | Assessment | Public | USFS |  | Partially Completed | 50001 | 250000 | Partially funded
Upper Little Truckee Basin | Bickford Meadows Watershed Assessment | Assessment | Private | TDLT |  | Not started | 0 | 50000 | Not funded
Upper Little Truckee Basin | Hwy 89 Little Truckee River Bridge | Design | Public | USFS |  | Not started | 1000001 | 2000000 | Not funded
Upper Little Truckee Basin | Lacey Meadow | Acquistion | Public | TDLT, USFS | TDLT | Completed | 2000001 | + | Fully funded
Upper Little Truckee Basin | Lacey Meadow | Assessment | Public | TDLT, USFS | TRWC | Completed | 0 | 50000 | Fully funded
Upper Little Truckee Basin | Lacey Meadow Drainage Renaturalization | Design | Public | TDLT |  | Not started | 0 | 50000 | Not funded
Upper Little Truckee Basin | Lacey Meadow Drainage Renaturalization | Implementation | Public | TDLT |  | Not started | 250001 | 500000 | Not funded
Upper Little Truckee Basin | Lacey Meadow Forest Management Plan | Design | Public | TDLT |  | Not started | 0 | 50000 | Not funded
Upper Little Truckee Basin | Lacey Meadow Forest Management Plan | Implementation | Public | TDLT |  | Not started | 0 | 50000 | Not funded
Upper Little Truckee Basin | Lacey Meadow Forest Management Plan | Post-Project Monitoring | Public | TDLT |  | Not started | 0 | 50000 | Not funded
Upper Little Truckee Basin | Lacey Meadow Grazing Management Plan | Design | Public | TDLT |  | Not started | 0 | 50000 | Not funded
Upper Little Truckee Basin | Lacey Meadow Grazing Management Plan | Post-Project Monitoring | Public | TDLT |  | Not started | 0 | 50000 | Not funded
Upper Little Truckee Basin | Lacey Meadow Grazing Management Plan - Long Term | Implementation | Public | TDLT |  | Not started | 0 | 50000 | Not funded
Upper Little Truckee Basin | Lacey Meadow Grazing Management Plan - Short Term | Implementation | Public | TDLT |  | Not started | 0 | 50000 | Not funded
Upper Little Truckee Basin | Lacey Meadow Lake Level Management and Mitigation | Design | Public | TDLT |  | Not started | 0 | 50000 | Not funded
Upper Little Truckee Basin | Lacey Meadow Lake Level Management and Mitigation | Implementation | Public | TDLT |  | Not started | 0 | 50000 | Not funded
Upper Little Truckee Basin | Lacey Meadow Lower Meadow Restoration | Design | Public | TDLT |  | Not started | 0 | 50000 | Not funded
Upper Little Truckee Basin | Lacey Meadow Lower Meadow Restoration | Design | Public | TDLT |  | Not started | 0 | 50000 | Not funded
Upper Little Truckee Basin | Lacey Meadow Lower Meadow Restoration | Implementation | Public | TDLT |  | Not started | 50001 | 100000 | Not funded
Upper Little Truckee Basin | Lacey Meadow Recreation Management Plan | Design | Public | TDLT |  | Not started | 0 | 50000 | Not funded
Upper Little Truckee Basin | Lacey Meadow Recreation Management Plan | Implementation | Public | TDLT |  | Not started | 0 | 50000 | Not funded
Sub Basin | Project Name | Project Type | Property Type | Landowner /Mgr | Financial Partners | Status | Cost Low | Cost High | Funding Status
Upper Little Truckee Basin | Lacey Meadow Recreation Management Plan | Post-Project Monitoring | Public | TDLT |  | Not started | 0 | 50000 | Not funded
Upper Little Truckee Basin | Lacey Meadow Upper Meadow Restoration | Design | Public | TDLT |  | Not started | 0 | 50000 | Not funded
Upper Little Truckee Basin | Lacey Meadow Upper Meadow Restoration | Implementation | Public | TDLT |  | Not started | 50001 | 100000 | Not funded
Upper Little Truckee Basin | LCT Reintroduction | Design | Public | USFS, TDLT USFWS |  | Not started | 500001 | 100000 | Not funded
Upper Little Truckee Basin | LCT Reintroduction | Implementation | Public | USFS, TDLT USFWS |  | Not started | 50001 | + | Not funded
Upper Little Truckee Basin | Outback Watershed Improvement Project | Design | Public | USFS | USFS | Completed |  |  | Fully funded
Upper Little Truckee Basin | Outback Watershed Improvement Project | Implementation | Public | USFS | USFS | Partially Completed |  |  | Partially funded
Upper Little Truckee Basin | Perazzo Meadows | Implementation | Public | USFS | TRWC, USFS | Partially Completed | 500001 | 1000000 | Partially funded
Upper Little Truckee Basin | Phoenix Project | Implementation | Public | USFS |  | Not started | 0 | 50000 | Not funded
Upper Little Truckee Basin | Phoenix Project | Design | Public | USFS | USFS | Completed | 0 | 50000 | Fully funded
Upper Little Truckee Basin | Sierra 89 Paired Wildlife Crossing Structures | Implementation | Public | Caltrans DOT |  | Not started |  |  | Fully funded
Upper Little Truckee Basin | Sierra 89 Wildlife Undercrossing Phase 1 | Implementation | Public | Caltrans DOT |  | Completed |  |  | Fully funded
Upper Little Truckee Basin | Sierra 89 Wildlife Undercrossing Phase 2 | Implementation | Public | Caltrans DOT |  | Partially Completed |  |  | Fully funded
Upper Little Truckee Basin | Underground Water storage | Assessment | Both | USFS |  | Not started | 0 | 50000 | Not funded
Upper Little Truckee Basin | Upper Little Truckee River Braiding | Design | Both | USFS |  | Not started |  |  | Not funded
Upper Little Truckee Basin | Upper Little Truckee Watershed | Assessment | Private | TDLT |  | Partially Completed | 50001 | 500000 | Partially funded
Upper Little Truckee Basin | Willow Flycatcher Post-Monitoring | Post-Project Monitoring | Public | USFS | UCSF, USFS